## AID Log
N | Action / Issue / Decision | Description | Owner | Due Date | Status | Comments
1 | Request additional budget - Future Scope | Approval on additional budget to be requested to ABC Bank CFO. | ABS Bank CFO | 2023-04-05 | Completed
2 | Project Issue: additional budget not approved | Additional budget Not approved by ABC Bank CFO. Project team need to identify a solution. | EM/TPM | 2023-04-10 | Completed | Resolved
3 | Workload increase vs external cost to be compared for ABC Bank | EM/TPM to estimate the workload increase in the voice bot enhancement, if the open source SDKs/APIs or clound infrastructure is not recommended. | EM/TPM | 2023-04-23 | Ongoing
4 | Decision to be confirmed for Locale support: internal vs external option | ABC Bank CFO to confirm if budget will be provided for user accesses for external employees or the work will be performed internally, increasing the workload by 2 days per week for 1 employee. | ABS Bank CFO | 2023-04-28 | Ongoing
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Dependencies
N | Dependency | Description | Owner | Due Date | Status | Comments
1 | Cloud Infrastructure and Open source SDKs/APIS | Use of clound infrastructure and open source SDKs/APIs need to be confirmed. | PM | 2023-04-15 | Ongoing
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Risk Log
N | Risk | Description | Severity | Probabilty of Occurrence | Contingency and Mitigation Actions (incl. "Plan B")
1 | Voice Profiling | Creating a knowledge base of customer voice profile to identify their emotions and validate the users. | Medium | Medium | 1) Capture user voice print to identify the correct user, validate and authorize; 2) Create voice print knowledge data base; 3) Define metrics to monitor unauthorised user requests; 4) Enhance dialog management;
2 | Data Theft | Customer calls can be hacked to steal Data. | High | Medium | 1) Implement 2-Factor Authentication for users. 2) Voice Bot Network security needs to be monitored and enhanced. 3) Priodically track security attacks and improve the firewall layer;
3 | Cyber Security | Voice Bot can be hacked making the user data at risk. | High | High | 1) Implement 2-Factor Authentication for users. 2) Voice Bot Network security needs to be monitored and enhanced. 3) Priodically track security attacks and improve the firewall layer;
4
5
6
7
8
9
10
11
12