## Risk LOG
N | Risk | Description | Severity | Probabilty of Occurrence | Contingency and Mitigation Actions (incl. "Plan B")
1 | Voice Profiling | Creating a knowledge base of customer voice profile to identify their emotions and validate the users. | Medium | Medium | 1) Capture user voice print to identify the correct user, validate and authorize; 2) Create voice print knowledge data base; 3) Define metrics to monitor unauthorised user requests; 4) Enhance dialog management;
2 | Data Theft | Customer calls can be hacked to steal Data. | High | Medium | 1) Implement 2-Factor Authentication for users. 2) Voice Bot Network security needs to be monitored and enhanced. 3) Priodically track security attacks and improve the firewall layer;
3 | Cyber Security | Voice Bot can be hacked making the user data at risk. | High | High | 1) Implement 2-Factor Authentication for users. 2) Voice Bot Network security needs to be monitored and enhanced. 3) Priodically track security attacks and improve the firewall layer;
4
5
6
7
8
9
10
11
12
Risk Log

## Definitions
Severity | Description
Low | Minimal impact to the project, not critial to project deliverables
Medium | Will impact the project in terms of timeline, cost, quality etc, however, the project will still move forward
High | Will jepordize the project or bring the project to a halt
Probability of Occurrence | Description
Low Risk | Very unlikely and unlikely to occur.
Medium Risk | May occur about half the time.
High Risk | Likely or very likely to occur.