## Project Charter
Project Information
Project Name | Voice Bot ABC Bank |  | ID Number | VB_AbcB1.0
Project Description | Develop a conversational voice bot to answer informational and transactional requests.
Project Sponsor | ABC Bank
Program Manager | Udaya Kiran
Project Manager | MK
Organization(s) | interface.ai
Target Start Date | 2023-04-10 | Target End Date: | 2023-07-05
Business Need / Project Goal
Develop a conversational voice bot that will answer both informational ( Example: What is the routing number/IFSC Code?) and transactional( Example: What is my balance?) customer requests. If the voice bot is unable to answer, voice bot should transfer the call to a call center queue.
Project Scope
In Scope |  |  | Out of Scope
Develop a conversational voice bot that will answer both informational and transactional customer requests. If the voice bot is unable to answer, voice bot should transfer the call to a call center queue. |  |  | ChatGPT Integration, Voice Profiling
Constraints | Voice Profiling Data Base
Key Risks | Cyber Security, Voice Print
Assumptions | Use of Cloud Infrastructure and Open source SDKs and API allowed
Project Budget | [To be updated ]
Project Team |  | Key Project Milestones
Name | Role | 1 | Address Transactional Request
Dev Team Member 1 | Developer | 2 | Address Informational Request
Dev Team Member 2 | Developer | 3 | Success Criteria Achieved
Dev Team Member 3 | Developer | 4 | Project Closure Sign-off
Dev Team Member 4 | Developer
Dev Team Member 5 | Developer
Dev Team Member 6 | QA
Project Charter