## Gantt Chart (months)
|  |  |  | 2023 | [11 empty] | 2024
N | Activity | Start Date | End Date | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
1 | Requirements definition | 2023-04-10 | 2023-04-15
2 | Project Kick Off | 2023-04-17 | 2023-04-17
3 | System development | 2023-04-17 | 2023-05-12
4 | Integration Testing | 2023-05-15 | 2023-05-20
5 | User Acceptance Testing | 2023-05-22 | 2023-05-26
6 | Rollout to business units | 2023-05-29 | 2023-06-02
7 | Support period | 2023-06-02 | 2023-07-05
8 | Project closure | 2023-07-06 | 2023-07-11
Status
Not Started
In Progress
Complete
Blocked

## Gantt Chart (weeks)
N | Activity | Assigned To | Start Date | End Date | Status | % Done | 2023
[7 empty] | April |  |  | May |  |  |  |  | June |  |  |  | July
[7 empty] | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24
1 | Requirements definition | TPM/EM | 2023-04-10 | 2023-04-15 | In Progress | 70% | bar: 2023-04-10
1.1 | Requirements gathering | TPM/EM | 2023-04-10 | 2023-04-13 | Complete | 100% | bar: 2023-04-10
1.2 | Identify the key features of the bot | TPM/EM | 2023-04-13 | 2023-04-14 | Complete | 100% | bar: 2023-04-10
1.3 | Determine the requirements for voice response functionality | TPM/EM | 2023-04-14 | 2023-04-14 | In Progress | 40% | bar: 2023-04-10
1.4 | Define the scope of the project | TPM/EM | 2023-04-14 | 2023-04-14 | In Progress | 60% | bar: 2023-04-10
2 | Project Kick Off | TPM/EM | 2023-04-17 | 2023-04-17 | Not Started | bar: 2023-04-17
3 | System development [Sprint 1 and Sprint 2] | Dev Team | 2023-04-17 | 2023-05-12 | Not Started | bar: 2023-04-17 to 2023-05-08
3.1 | Develop user intents modules for Information and Transactional Request | Developer | 2023-04-17 | 2023-04-28 | Not Started | bar: 2023-04-17 to 2023-04-24
3.2 | Develop the conversation script for voice response functionality | Developer | 2023-04-17 | 2023-04-28 | Not Started | bar: 2023-04-17 to 2023-04-24
3.3 | Develop voice response functionality using the selected technologies | Developer | 2023-04-17 | 2023-04-28 | Not Started | bar: 2023-04-17 to 2023-04-24
3.4 | Implement the UI design for the bot | Developer | 2023-04-17 | 2023-04-28 | Not Started | bar: 2023-04-17 to 2023-04-24
3.5 | Develop enhanced user intents modules | Developer | 2023-05-01 | 2023-05-12 | In Progress | 20% | bar: 2023-05-01 to 2023-05-08
3.6 | Set up the necessary authentication and security measures | Developer | 2023-05-01 | 2023-05-12 | Not Started | bar: 2023-05-01 to 2023-05-08
3.7 | Develop logging and monitoring services | Developer | 2023-05-01 | 2023-05-12 | Not Started | bar: 2023-05-01 to 2023-05-08
3.8 | Deploy the bot to a cloud hosting provider | Developer | 2023-05-01 | 2023-05-12 | Not Started | bar: 2023-05-01 to 2023-05-08
4 | Integration Testing | QA | 2023-05-15 | 2023-05-20 | Not Started | bar: 2023-05-15
5 | User Acceptance Testing | QA | 2023-05-22 | 2023-05-26 | Not Started | bar: 2023-05-22
6 | Rollout to business units | TPM/EM | 2023-05-29 | 2023-06-02 | Not Started | bar: 2023-05-29
6.1 | User Training | TPM/EM | 2023-05-29 | 2023-05-30 | Not Started | bar: 2023-05-29
6.2 | Gather feedback and Implement Issues | TPM/EM | 2023-05-31 | 2023-06-01 | Not Started | bar: 2023-05-29
6.3 | Cutover & Go Live | TPM/EM | 2023-06-02 | 2023-06-02 | Not Started | bar: 2023-05-29
7 | Support period | Dev Team | 2023-06-02 | 2023-07-05 | Not Started | bar: 2023-06-05
8 | Project closure | TPM/EM | 2023-07-06 | 2023-07-11 | Not Started | bar: 2023-06-05