## RACI
Activity / Deliverable | Project Sponsor | Engineering Manager/Product Owner | Dev Team | Engineering Manager/TPM | Program Director | Engineering Manager/ TPM
| PMO |  | Dev Team |  | Product Release
Project Management
Requirements gathering | C | A/R |  |  | I
Project Planning and Kick-Off | C | A/R | C |  | C
Weekly Status Report | I | A/R |  | C | I
Work-Sprint 1: System Development
Develop user intents modules for Information and Transactional Request |  |  | R | A | I
Develop the conversation script for voice response functionality |  |  | R | A | I
Develop voice response functionality using the selected technologies |  |  | R | A | I
Implement the UI design for the bot |  |  | R | A | I
Integration Testing & User Acceptance Testing |  |  | R | A | I
Project Demo | I | I | R | A/R | C/I
Work-Sprint 2: System Development
Develop enhanced user intents modules |  |  | R | A | I
Set up the necessary authentication and security measures |  |  | R | A | I
Develop logging and monitoring services |  |  | R | A | I
Deploy the bot to a cloud hosting provider |  |  | R | A | I
Integration Testing & User Acceptance Testing |  |  | R | A | I
Project Demo | I | I | R | A/R | C/I
Rollout To Business Unit
User Training | I | I | R |  | I | A/R
Go Live | I | I | R |  | I | A/R
Support Period
Project Support | I | I | R | A/R | I | A/R
Project Closure
Project Closure Sign-off and Release Resources | I | A |  | R | I | A/R
R - Responsible
A - Accountable
C - Consulted
I - Informed
"RACI" Matrix