## Resource Availability
Task - Sprint 1 | Responsible | Duration (est. in days) | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30
|  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Develop user intents modules for Information and Transactional Request | Developer 1 | 7.5 | 1 | 1 | 1 | 0.75 | 1 |  |  | 1 | 1 | Adhoc/Production-Issue |  | 0.75
Develop the conversation script for voice response functionality | Developer 2 | 9.75 | 1 | 1 | 0.75 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
Develop voice response functionality using the selected technologies | Developer 3 | 6 | 2023-04-17: 1; 2023-04-18: 1; 2023-04-19: 1; 2023-04-20: Vacation; 2023-04-24: Adhoc/Production-Issue; 2023-04-26: 1; 2023-04-27: 1; 2023-04-28: 1
Integration Testing & User Acceptance Testing | QA 1 | 8 | 1 | 1 | 1 | 1 | 1 |  |  | Other Assignment |  | 1 | 1 | 1
Project Demo & FeedBack Implementations | DevTeam/ EM/TPM | 7.5 | Other Assignment |  | 1 | 0.75 | 1 |  |  | 1 | 1 | 1 | 0.75 | 1
Task - Sprint 2 | Responsible | Duration (est. in days) | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14
|  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Develop enhanced user intents modules | Developer 1 | 8 | 1 | 1 | 1 | 1 | 1 |  |  | Adhoc/Production-Issue |  | 1 | 1 | 1
Set up the necessary authentication and security measures | Developer 2 | 7.5 | 1 | 1 | 0.75 | 1 | 1 |  |  | 1 | 0.75 | Vacation |  | 1
Develop logging and monitoring services | Developer 3/EM | 9 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 0.5 | 0.5 | 1
Deploy the bot to a cloud hosting provider | Developer 4/DevOps | 8 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | Adhoc/Production-Issue |  | 1
Integration Testing & User Acceptance Testing | QA | 7.5 | 1 | 1 | 1 | Other Assignment |  |  |  | 1 | 1 | 0.5 | 1 | 1
Project Demo & FeedBack Implementations | Dev Team/ EM/TPM | 5 | 2023-05-01: Other Assignment; 2023-05-03: 1; 2023-05-04: 1; 2023-05-05: 0.5; 2023-05-08: 1; 2023-05-09: 1; 2023-05-10: Other Assignment; 2023-05-12: 0.5
Resource Planning